## Sheet
ID | Milestone Description | Department/Owner | Target Month | Scheduled Deadline | Actual Completion Date | Status | Notes/Comments
001 | Project Kickoff Meeting | Project Management | January | 2024-01-15 | 2024-01-14 | Completed | Finished ahead of schedule.
002 | Market Research Report | Marketing | February | 2024-02-10 | 2024-02-12 | Completed | Delayed by 2 days due to data collection.
003 | UI/UX Design Approval | Design | March | 2024-03-05 | 2024-03-05 | Completed | Approved by stakeholders on first review.
004 | Beta Version Release | Engineering | April | 2024-04-20 |  | In Progress | On track for scheduled date.
005 | Security Audit | IT/Compliance | May | 2024-05-15 |  | Pending | Vendor selection in progress.