## Sheet
Task ID | Feature / Task Description | Category | Owner | Status | Completion Date | Notes
PR-001 | Final QA Regression Testing | Quality Assurance | Jane Doe | Completed | 2023-10-25 | All critical bugs resolved.
PR-002 | Documentation Update | Technical Writing | John Smith | Completed | 2023-10-26 | User guides updated for v2.0.
PR-003 | Server Deployment Script | DevOps | Mike Ross | In Progress | - | Pending final approval.
PR-004 | Marketing Asset Review | Marketing | Sarah Chen | Completed | 2023-10-27 | Social media kits ready.
PR-005 | Security Vulnerability Scan | Security | Alex Kim | Pending | - | Scheduled for tomorrow.