## Sheet
ID | Task Description | Phase | Assigned To | Start Date | End Date | Duration (Days) | Status | Budget Est.
PHASE 1: PRE-CONSTRUCTION & PERMITS
1.1 | Architectural Blueprints | Planning | Lead Architect | 2023-11-01 | 2023-11-15 | 14 | Complete | $2,500
1.2 | City Building Permits | Legal | Project Manager | 2023-11-16 | 2023-12-10 | 24 | Complete | $850
PHASE 2: DEMOLITION & SITE PREP
2.1 | Interior Wall Demolition | Demo | Demo Crew | 2024-01-05 | 2024-01-10 | 5 | In Progress | $1,200
2.2 | Waste Removal & Bin Rental | Demo | Waste Mgmt Co. | 2024-01-05 | 2024-01-12 | 7 | In Progress | $600
PHASE 3: STRUCTURAL & MECHANICAL
3.1 | Rough-in Electrical | Mechanical | Certified Electric | 2024-01-15 | 2024-01-20 | 5 | Not Started | $3,200
3.2 | Rough-in Plumbing | Mechanical | FlowRight Plumbing | 2024-01-15 | 2024-01-22 | 7 | Not Started | $2,800
3.3 | Framing & Structural Support | Framing | General Contractor | 2024-01-23 | 2024-02-05 | 13 | Not Started | $4,500
PHASE 4: FINISHING
4.1 | Drywall Installation & Taping | Finishing | Drywall Specialists | 2024-02-10 | 2024-02-20 | 10 | Not Started | $2,100
4.2 | Painting & Trim | Finishing | Interior Decor Ltd. | 2024-02-22 | 2024-03-05 | 11 | Not Started | $1,800
4.3 | Flooring Installation | Finishing | Floor Master | 2024-03-06 | 2024-03-15 | 9 | Not Started | $5,000