## Sheet
Project ID | Project Name | Task Owner | Priority | Status | Start Date | End Date | % Complete | Budget Status | Notes
P001 | Website Redesign | John Doe | High | In Progress | 2023-10-01 | 2023-12-15 | 45% | On Track | Design phase nearly complete.
P002 | Q4 Marketing Campaign | Jane Smith | Medium | Not Started | 2023-11-01 | 2023-12-31 | 0% | Pending | Waiting for asset approval.
P003 | Inventory System Update | Mike Ross | High | Completed | 2023-08-15 | 2023-09-30 | 100% | Under Budget | Migration successful.
P004 | Client Onboarding Portal | Sarah Connor | Low | On Hold | 2023-09-01 | 2024-01-10 | 20% | At Risk | Resources diverted to P001.
P005 | Annual Security Audit | Robert Brown | High | In Progress | 2023-10-10 | 2023-11-20 | 60% | On Track | No major issues identified yet.