## Sheet
Task Name | Assigned To | Priority | Status | Due Date | Progress (%) | Notes
Project Kickoff Meeting | Alice Johnson | High | Completed | 2023-10-01 | 100% | Minutes shared in drive.
UI Design Mockups | Bob Smith | High | In Progress | 2023-10-15 | 60% | Waiting for branding guidelines.
Database Schema Setup | Charlie Davis | Medium | Not Started | 2023-10-20 | 0% | Awaiting server access.
Content Strategy | Dana White | Low | In Progress | 2023-10-25 | 30% | Drafting blog post topics.
Final Quality Audit | Alice Johnson | High | Not Started | 2023-11-05 | 0% | Scheduled for final week.