## Sheet
Job ID | Deliverable Name | Assigned To | Start Date | Target End Date | Actual End Date | Status | Completion (%) | Notes
J-001 | Project Proposal | John Doe | 2023-10-01 | 2023-10-05 | 2023-10-04 | Completed | 100% | Approved by client.
J-002 | Initial Wireframes | Jane Smith | 2023-10-06 | 2023-10-12 |  | In Progress | 60% | Waiting on feedback for homepage.
J-003 | Database Schema | Mike Ross | 2023-10-10 | 2023-10-15 |  | Not Started | 0% | Pending wireframe approval.