## Sheet
Milestone ID | Milestone Description | Owner | Start Date | Target Date | Completion Date | Status | Progress (%)
M-01 | Project Kickoff & Charter | Project Manager | 2023-10-01 | 2023-10-05 | 2023-10-04 | Completed | 100%
M-02 | Market Research Analysis | Lead Analyst | 2023-10-06 | 2023-10-20 | - | In Progress | 65%
M-03 | Product Design Mockups | UI/UX Designer | 2023-10-21 | 2023-11-05 | - | Not Started | 0%
M-04 | Prototype Development | Dev Team | 2023-11-06 | 2023-12-01 | - | Not Started | 0%
M-05 | User Acceptance Testing | QA Lead | 2023-12-02 | 2023-12-15 | - | Not Started | 0%
M-06 | Final Launch | Stakeholders | 2023-12-20 | 2023-12-31 | - | Not Started | 0%