## Sheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Status | % Complete | Notes
1.1 | Project Kick-off Meeting | Project Manager | 2023-11-01 | 2023-11-01 | 1 | Completed | 100% | All stakeholders attended
1.2 | Requirements Gathering | Business Analyst | 2023-11-02 | 2023-11-15 | 14 | In Progress | 60% | Pending final client sign-off
2.1 | System Design Phase | Lead Architect | 2023-11-16 | 2023-11-30 | 15 | Not Started | 0% | Awaiting requirements completion
3.1 | Development Sprint 1 | Dev Team | 2023-12-01 | 2023-12-15 | 15 | Not Started | 0% | Backlog items defined
4.1 | User Acceptance Testing | QA Team | 2023-12-16 | 2023-12-30 | 15 | Not Started | 0% | Test cases drafted