## Sheet
Phase | Task Description | Owner | Start Date | End Date | Status | % Complete | Notes
Initiation | Project Charter Approval | John Doe | 2023-10-01 | 2023-10-05 | Completed | 100% | Signed by sponsor.
Planning | Resource Allocation | Jane Smith | 2023-10-06 | 2023-10-10 | In Progress | 60% | Pending final budget review.
Planning | Risk Management Plan | Mike Ross | 2023-10-08 | 2023-10-12 | Not Started | 0% | Waiting for resource list.
Execution | Development Phase 1 | Dev Team | 2023-10-15 | 2023-11-15 | In Progress | 25% | Sprint 1 ongoing.
Execution | Quality Assurance Testing | QA Team | 2023-11-16 | 2023-11-30 | On Hold | 0% | Dependent on Dev Phase 1.
Closing | Project Handover | John Doe | 2023-12-01 | 2023-12-05 | Not Started | 0% | -