## Sheet
ID | Action Item Description | Priority | Owner | Status | Due Date | Notes / Comments
101 | Finalize project charter and scope | High | John Doe | In Progress | 2023-11-01 | Pending stakeholder approval on section 3.
102 | Source vendor quotes for hardware | Medium | Jane Smith | Not Started | 2023-11-05 | Require minimum of 3 quotes.
103 | Weekly team sync meeting | Low | Team | Completed | 2023-10-25 | Minutes uploaded to shared drive.
104 | Security audit remediation | High | Mike Ross | Blocked | 2023-11-10 | Waiting on IT access permissions.
105 | Draft user documentation | Medium | Sarah Lee | In Progress | 2023-11-15 | Focusing on installation guide first.