## Sheet
Task ID | Task Description | Assignee | Priority | Status | Start Date | Due Date | % Complete | Comments
101 | Project Kick-off Meeting | Sarah Miller | High | Completed | 2023-10-01 | 2023-10-01 | 100% | All stakeholders attended.
102 | Market Research Analysis | John Doe | Medium | In Progress | 2023-10-02 | 2023-10-15 | 45% | Waiting for final survey data.
103 | UI/UX Prototype Design | Emma Wilson | High | Not Started | 2023-10-10 | 2023-10-25 | 0% | Pending project brief approval.
104 | Content Strategy Review | Robert Chen | Low | In Review | 2023-10-05 | 2023-10-12 | 90% | Final edits requested by PM.
105 | Database Migration | Alex Smith | High | In Progress | 2023-10-08 | 2023-10-20 | 30% | Testing backup scripts.