## Sheet
Milestone ID | Milestone Name | Description | Responsible Party | Start Date | Target End Date | Actual Completion Date | Status | % Complete | Notes
M1 | Project Kickoff | Initial meeting and scope definition | Project Manager | 2023-10-01 | 2023-10-02 | 2023-10-02 | Completed | 100% | All stakeholders attended.
M2 | Design Phase | UI/UX wireframes and approval | Design Lead | 2023-10-05 | 2023-10-20 |  | In Progress | 60% | Awaiting feedback on mobile mockups.
M3 | Development Sprint 1 | Core backend infrastructure | Engineering Team | 2023-10-21 | 2023-11-15 |  | Not Started | 0% | Dependent on Design Phase.
M4 | Beta Testing | Internal user acceptance testing | QA Team | 2023-11-20 | 2023-12-05 |  | Not Started | 0%
M5 | Final Deployment | Go-live on production server | DevOps | 2023-12-10 | 2023-12-12 |  | Not Started | 0%