## Sheet
Milestone ID | Task / Deliverable Name | Assigned To | Start Date | Due Date | Status | % Complete | Notes & Comments
M1-001 | Project Kick-off & Planning | Project Manager | 2023-10-01 | 2023-10-05 | Completed | 100% | Initial stakeholders meeting finalized.
M1-002 | Requirement Gathering | Business Analyst | 2023-10-06 | 2023-10-20 | In Progress | 65% | Interviews with department heads ongoing.
M1-003 | System Design & Architecture | Lead Architect | 2023-10-21 | 2023-11-05 | Not Started | 0% | Pending requirement sign-off.
M2-001 | Database Schema Development | DB Admin | 2023-11-06 | 2023-11-15 | Not Started | 0%
M2-002 | Core API Implementation | Dev Team | 2023-11-16 | 2023-12-15 | Not Started | 0%