## Sheet
Task ID | Task Name | Assignee | Start Date | End Date | Duration (Days) | Status | Priority | % Complete | Notes
1.1 | Project Kickoff | Project Manager | 2023-10-01 | 2023-10-01 | 1 | Completed | High | 100% | Initial stakeholder meeting
1.2 | Requirements Gathering | Business Analyst | 2023-10-02 | 2023-10-08 | 7 | In Progress | High | 60% | Interviewing department heads
1.3 | Design Phase | Lead Designer | 2023-10-09 | 2023-10-20 | 12 | Not Started | Medium | 0% | UI/UX wireframes
1.4 | Development Sprint 1 | Dev Team | 2023-10-21 | 2023-11-04 | 14 | Not Started | High | 0% | Core backend infrastructure
1.5 | Quality Assurance | QA Lead | 2023-11-05 | 2023-11-12 | 7 | Not Started | Medium | 0% | Bug tracking and stress tests
1.6 | User Acceptance Testing | Product Owner | 2023-11-13 | 2023-11-20 | 7 | Not Started | High | 0% | Final sign-off before launch