## Sheet
ID | Task Description | Owner | Priority | Start Date | Due Date | Status | Completion % | Notes
101 | Finalize project budget proposal | John Doe | High | 2023-10-23 | 2023-10-25 | In Progress | 50% | Awaiting final quotes from vendors.
102 | Update client presentation slides | Jane Smith | Medium | 2023-10-24 | 2023-10-26 | Completed | 100% | Slides uploaded to shared drive.
103 | Weekly team sync meeting | All Team | Low | 2023-10-27 | 2023-10-27 | Not Started | 0% | Scheduled for Friday morning.
104 | Security audit remediation | Mike Ross | High | 2023-10-23 | 2023-10-30 | Delayed | 20% | Pending access permissions to server.
105 | Order new office supplies | Sarah Lee | Low | 2023-10-25 | 2023-10-27 | In Progress | 10% | Cataloging current inventory.