## Sheet
ID | Task Description | Assigned Contractor | Start Date | End Date | Duration (Days) | % Complete | Status | Budgeted Cost | Actual Cost
1.1 | Site Clearance & Excavation | Groundworks Ltd. | 2023-10-01 | 2023-10-10 | 10 | 100% | Complete | $5,000 | $5,200
1.2 | Foundation Pouring | Concrete Solutions | 2023-10-12 | 2023-10-18 | 6 | 100% | Complete | $12,000 | $11,500
2.1 | Structural Steel Framing | IronMasters Co. | 2023-10-20 | 2023-11-05 | 16 | 45% | In Progress | $25,000 | $10,000
2.2 | Roofing Installation | TopShield Roofing | 2023-11-06 | 2023-11-15 | 9 | 0% | Delayed | $8,500 | $0
3.1 | Electrical Rough-in | BrightVolt Electric | 2023-11-10 | 2023-11-20 | 10 | 0% | Pending | $6,000 | $0
3.2 | Plumbing Rough-in | FlowRight Pipes | 2023-11-12 | 2023-11-22 | 10 | 0% | Pending | $5,500 | $0