## Sheet
ID | Milestone Description | Phase | Responsible Party | Start Date | Target End Date | Actual End Date | % Complete | Status | Budget Status
1.0 | Site Acquisition & Permits | Pre-Construction | Project Manager | 2023-09-01 | 2023-10-15 | 2023-10-12 | 100% | Completed | On Track
2.0 | Foundation & Excavation | Construction | Site Engineer | 2023-10-20 | 2023-12-05 | - | 85% | In Progress | Over Budget
3.0 | Structural Framing | Construction | Framing Contractor | 2023-12-10 | 2024-02-15 | - | 10% | In Progress | On Track
4.0 | Roofing & External Cladding | Construction | General Contractor | 2024-02-20 | 2024-03-30 | - | 0% | Not Started | Pending
5.0 | Electrical & Plumbing Rough-in | Systems | MEP Subcontractor | 2024-03-01 | 2024-04-15 | - | 0% | Delayed | On Track
6.0 | Interior Finishing | Finishing | Interior Designer | 2024-04-20 | 2024-06-15 | - | 0% | Not Started | Pending
7.0 | Final Inspection & Handover | Close-out | Compliance Officer | 2024-06-20 | 2024-07-01 | - | 0% | Not Started | Pending