## Sheet
Project Phase Status Tracker
Project Name | Phase | Assigned To | Start Date | Target Date | Status | % Complete
Website Redesign | Discovery & Planning | Jane Doe | 2023-10-01 | 2023-10-15 | Completed | 100%
Website Redesign | UI/UX Design | John Smith | 2023-10-16 | 2023-11-05 | In Progress | 65%
Mobile App Update | API Integration | Alex Rivera | 2023-11-01 | 2023-11-20 | On Hold | 20%
Security Audit | Risk Assessment | Sarah Chen | 2023-11-10 | 2023-11-15 | Not Started | 0%
Cloud Migration | Data Backup | Mike Wilson | 2023-10-25 | 2023-10-28 | Delayed | 45%