## Sheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | % Complete | Status
1.1 | Project Initiation & Planning | John Doe | 2023-10-01 | 2023-10-05 | 5 | 100% | Completed
1.2 | Requirement Analysis | Jane Smith | 2023-10-06 | 2023-10-15 | 10 | 80% | On Track
2.1 | System Design | Mike Ross | 2023-10-16 | 2023-10-25 | 10 | 20% | Delayed
2.2 | Database Architecture | Sarah Connor | 2023-10-20 | 2023-10-30 | 11 | 0% | Not Started
3.1 | Frontend Development | Alex Vance | 2023-11-01 | 2023-11-20 | 20 | 0% | Planned