## Sheet
ID | Task Description | Assigned To | Priority | Status | Due Date | Notes
1 | Define project requirements | Jane Doe | High | Completed | 2023-10-01 | Initial stakeholder meeting finished.
2 | Design system architecture | John Smith | High | In Progress | 2023-10-15 | Reviewing cloud provider options.
3 | Develop UI wireframes | Alice Wong | Medium | Not Started | 2023-10-20 | Waiting for brand guidelines.
4 | Setup CI/CD pipeline | Bob Miller | Medium | In Progress | 2023-10-25 | GitHub Actions configuration.
5 | Beta testing phase 1 | Quality Team | Low | Not Started | 2023-11-05 | Dependent on task 2 and 4.