## Sheet
Task ID | Activity Description | Assigned To | Priority | Start Date | End Date | Status | % Complete
101 | Project Kick-off Meeting | John Doe | High | 2023-10-01 | 2023-10-01 | Completed | 100%
102 | UI/UX Design Phase | Jane Smith | Medium | 2023-10-02 | 2023-10-15 | In Progress | 65%
103 | Backend API Development | Mike Ross | High | 2023-10-05 | 2023-10-25 | In Progress | 40%
104 | QA Testing & Bug Fixes | Sarah Connor | Medium | 2023-10-26 | 2023-11-05 | Pending | 0%
105 | Deployment & Documentation | Chris Evans | Low | 2023-11-06 | 2023-11-10 | Pending | 0%