## Sheet
ID | Task Description | Assigned To | Priority | Status | Start Date | Deadline | % Done | Notes
101 | Design landing page wireframe | Sarah Miller | High | In Progress | 2023-10-24 | 2023-10-31 | 60% | Waiting for brand assets
102 | Database optimization | John Chen | Medium | Completed | 2023-10-20 | 2023-10-23 | 100% | Reduced query time by 40%
103 | Client feedback meeting | Alex Reed | High | Not Started | 2023-10-26 | 2023-10-26 | 0% | Prepare slides beforehand
104 | Security audit | Team Lead | Low | In Progress | 2023-10-22 | 2023-11-05 | 25% | Quarterly routine check
105 | Update documentation | Sarah Miller | Low | Not Started | 2023-10-27 | 2023-10-30 | 0% | Focus on API endpoints