## Sheet
ID | Task Description | Assigned Contractor | Start Date | End Date | Duration (Days) | % Complete | Status
1.1 | Site Clearing & Excavation | Groundworks Ltd | 2023-10-01 | 2023-10-10 | 10 | 100% | Completed
1.2 | Foundation Pouring | Concrete Masters | 2023-10-11 | 2023-10-20 | 10 | 100% | Completed
2.1 | Structural Framing | Build-Right Corp | 2023-10-21 | 2023-11-15 | 25 | 65% | In Progress
2.2 | Roofing & Trusses | Top Peak Roofing | 2023-11-16 | 2023-11-25 | 10 | 0% | Not Started
3.1 | Electrical Rough-in | Sparky Solutions | 2023-11-10 | 2023-11-20 | 11 | 10% | Delayed
3.2 | Plumbing Installation | Flow-Rite Systems | 2023-11-12 | 2023-11-22 | 11 | 0% | Not Started
4.1 | Interior Drywall | Finish Line Interiors | 2023-11-26 | 2023-12-10 | 15 | 0% | Not Started
5.1 | Final Inspection | City Compliance Office | 2023-12-15 | 2023-12-16 | 2 | 0% | Not Started