## Sheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | % Complete | Status | Notes
1.1 | Site Clearing and Excavation | Groundworks Ltd | 2023-10-01 | 2023-10-10 | 10 | 100% | Completed | Inspected and cleared
1.2 | Foundation Pouring | BuildRight Co | 2023-10-12 | 2023-10-20 | 8 | 50% | In Progress | Delayed 2 days due to rain
2.1 | Structural Framing | Frame Masters | 2023-10-22 | 2023-11-05 | 14 | 0% | Not Started | Materials pending delivery
2.2 | Roofing Installation | Top Peak Roofing | 2023-11-06 | 2023-11-12 | 6 | 0% | Not Started
3.1 | Electrical Rough-in | Sparky Pros | 2023-11-15 | 2023-11-20 | 5 | 0% | Not Started