## Sheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Progress (%) | Priority
101 | Project Kick-off Meeting | Sarah Miller | 2023-10-01 | 2023-10-01 | Completed | 100% | High
102 | Requirement Analysis | James Chen | 2023-10-02 | 2023-10-10 | In Progress | 65% | High
103 | UI/UX Design Mockups | Elena Rodriguez | 2023-10-05 | 2023-10-20 | In Progress | 30% | Medium
104 | Database Schema Setup | David Smith | 2023-10-12 | 2023-10-15 | Not Started | 0% | Medium
105 | API Documentation | Sarah Miller | 2023-10-15 | 2023-10-25 | Not Started | 0% | Low