## Sheet
Task ID | Task Description | Assigned To | Priority | Start Date | Due Date | Status | % Complete
001 | Project Kick-off Meeting | John Doe | High | 2023-10-01 | 2023-10-01 | Completed | 100%
002 | Requirement Analysis | Jane Smith | High | 2023-10-02 | 2023-10-10 | In Progress | 60%
003 | UI/UX Design Mockups | Mike Ross | Medium | 2023-10-11 | 2023-10-20 | Not Started | 0%
004 | Database Architecture | Sarah Connor | High | 2023-10-05 | 2023-10-15 | In Progress | 30%
005 | Unit Testing Phase 1 | Steve Rogers | Low | 2023-10-21 | 2023-10-30 | Not Started | 0%