## Sheet
Task ID | Task Description | Assigned To | Priority | Start Date | Due Date | Status | Notes
001 | Project Kickoff Meeting | Sarah Jenkins | High | 2023-10-01 | 2023-10-01 | Completed | Meeting minutes uploaded to drive.
002 | Database Schema Design | Mark Chen | High | 2023-10-02 | 2023-10-05 | In Progress | Waiting on final requirements.
003 | User Interface Mockups | Elena Rodriguez | Medium | 2023-10-04 | 2023-10-10 | Not Started | Pending logo assets.
004 | API Documentation | David Smith | Low | 2023-10-06 | 2023-10-15 | Not Started | Internal use only.
005 | Security Audit | Sarah Jenkins | High | 2023-10-12 | 2023-10-20 | Not Started | External consultant required.