## Sheet
Milestone / Task Name | Owner | Priority | Start Date | Target Date | Status | % Complete | Notes
Project Kickoff Meeting | John Doe | High | 2023-10-01 | 2023-10-02 | Completed | 100% | All stakeholders attended.
Requirement Gathering | Jane Smith | High | 2023-10-03 | 2023-10-10 | In Progress | 60% | Waiting on feedback from the marketing team.
Initial Design Mockups | Mike Ross | Medium | 2023-10-11 | 2023-10-18 | Not Started | 0% | Pending requirement finalization.
Database Architecture Setup | Sarah Chen | High | 2023-10-05 | 2023-10-12 | Delayed | 20% | Server access issues encountered.
Weekly Progress Review | John Doe | Low | 2023-10-13 | 2023-10-13 | Planned | 0% | Scheduled for Friday afternoon.