## Sheet
Task ID | Task Description | Assigned To | Priority | Start Date | Deadline | Status | Progress (%) | Notes
001 | Project Proposal Draft | John Doe | High | 2023-10-01 | 2023-10-05 | Completed | 100% | Sent to manager for review.
002 | Client Feedback Integration | Jane Smith | Medium | 2023-10-06 | 2023-10-10 | In Progress | 45% | Waiting on final email from client.
003 | Budget Approval | Robert Brown | High | 2023-10-08 | 2023-10-12 | Not Started | 0% | Pending Q3 financial report.
004 | Marketing Asset Design | Emily White | Low | 2023-10-10 | 2023-10-20 | In Progress | 20% | Social media banners finished.
005 | Final Quality Audit | Michael Green | High | 2023-10-21 | 2023-10-25 | Not Started | 0% | Requires previous tasks completion.