## Sheet
Task ID | Category | Task Description | Assigned To | Start Date | Deadline | Status | Estimated Cost | Actual Cost | Notes
101 | Venue | Research and shortlist locations | Jane Doe | 2023-11-01 | 2023-11-10 | Completed | $0.00 | $0.00 | Top 3 choices identified
102 | Venue | Site visits and final selection | Jane Doe | 2023-11-12 | 2023-11-20 | In Progress | $100.00 | $50.00 | Travel expenses included
201 | Catering | Menu tasting and selection | John Smith | 2023-12-01 | 2023-12-05 | Not Started | $500.00 | $0.00 | Waiting for menu options
301 | Marketing | Social media teaser campaign | Alice Wong | 2023-11-15 | 2023-12-15 | In Progress | $1,200.00 | $400.00 | Daily posts scheduled
401 | Logistics | Equipment rental (Audio/Visual) | Bob Miller | 2024-01-10 | 2024-01-15 | Not Started | $2,500.00 | $0.00 | Quote pending