## Sheet
ID | Action Item / Task Description | Priority | Owner | Status | Due Date | Completion Date | Notes/Comments
101 | Initial project kickoff meeting | High | Project Manager | Completed | 2023-10-01 | 2023-10-01 | All stakeholders attended.
102 | Finalize resource allocation | Medium | Department Head | In Progress | 2023-10-15 |  | Pending budget approval.
103 | Quality assurance testing - Phase 1 | High | QA Lead | Not Started | 2023-11-01 |  | Requires hardware setup.
104 | Client feedback review | Low | Account Manager | Not Started | 2023-11-10 |  | To be scheduled after Phase 1.
105 | Final documentation delivery | Medium | Technical Writer | Not Started | 2023-12-01 |  | Drafting in progress.