## Sheet
Milestone ID | Milestone Description | Phase/Category | Owner | Planned Start | Target Finish | Actual Finish | Status | % Complete | Notes/Comments
M-01 | Project Kick-off Meeting | Initiation | Project Manager | 2023-10-01 | 2023-10-01 | 2023-10-01 | Completed | 100% | All stakeholders present.
M-02 | Requirements Finalization | Planning | Business Analyst | 2023-10-05 | 2023-10-15 |  | In Progress | 60% | Awaiting feedback on Phase 2.
M-03 | Design Sign-off | Design | Lead Designer | 2023-10-16 | 2023-10-30 |  | Not Started | 0% | Pending M-02.
M-04 | Core Development Complete | Execution | Lead Developer | 2023-11-01 | 2023-12-15 |  | Not Started | 0%
M-05 | User Acceptance Testing (UAT) | Testing | QA Lead | 2023-12-16 | 2023-12-31 |  | Not Started | 0%
M-06 | Final Deployment/Go-Live | Closure | Operations | 2024-01-05 | 2024-01-05 |  | Not Started | 0%