## Sheet
Task ID | Task Description | Assigned To | Priority | Status | Start Date | Due Date | % Complete | Notes
001 | Project Kick-off Meeting | Sarah Miller | High | Completed | 2023-11-01 | 2023-11-01 | 100% | All stakeholders attended
002 | Market Analysis Report | James Wilson | Medium | In Progress | 2023-11-02 | 2023-11-15 | 65% | Pending competitor data
003 | UI/UX Design Mockups | Anna Chen | High | Not Started | 2023-11-10 | 2023-11-25 | 0% | Waiting for brief approval
004 | Database Architecture | Robert Smith | High | In Progress | 2023-11-05 | 2023-11-20 | 40% | Schema drafting phase
005 | Content Strategy | Emily Blunt | Low | Not Started | 2023-11-20 | 2023-12-05 | 0%