## Sheet
Task ID | Task Description | Assigned To | Priority | Start Date | Due Date | Status | % Complete | Notes
101 | Project Kick-off Meeting | John Doe | High | 2023-10-01 | 2023-10-01 | Completed | 100% | All stakeholders attended.
102 | Requirement Analysis | Jane Smith | High | 2023-10-02 | 2023-10-10 | In Progress | 60% | Waiting on client feedback.
103 | UI/UX Design Mockups | Mike Ross | Medium | 2023-10-11 | 2023-10-20 | Not Started | 0% | Pending requirement sign-off.
104 | Database Schema Design | Sarah Connor | High | 2023-10-05 | 2023-10-12 | In Progress | 30% | -
105 | Environment Setup | Tech Team | Low | 2023-10-01 | 2023-10-03 | Completed | 100% | Server is live.