## Sheet
ID | Task Description | Assignee | Start Date | End Date | Priority | Status | % Complete
1 | Project Kick-off Meeting | John Doe | 2023-10-01 | 2023-10-01 | High | Completed | 100%
2 | Requirement Analysis | Jane Smith | 2023-10-02 | 2023-10-10 | High | In Progress | 60%
3 | UI/UX Design Mockups | Mike Ross | 2023-10-05 | 2023-10-15 | Medium | In Progress | 25%
4 | Database Architecture | Sarah Connor | 2023-10-12 | 2023-10-20 | High | Not Started | 0%
5 | Frontend Development | James Wilson | 2023-10-15 | 2023-11-05 | Medium | Not Started | 0%
6 | Backend API Integration | Jane Smith | 2023-10-20 | 2023-11-10 | High | Not Started | 0%