## Sheet
Task ID | Task Description | Category | Priority | Assignee | Status | Start Date | End Date | Est. Hours | Actual Hours
DEV-101 | Database Schema Design | Backend | High | John Doe | Completed | 2023-10-01 | 2023-10-03 | 12 | 10
DEV-102 | User Authentication API | Backend | High | Jane Smith | In Progress | 2023-10-04 | 2023-10-10 | 20 | 15
UI-201 | Dashboard UI Layout | Frontend | Medium | Mike Ross | In Progress | 2023-10-05 | 2023-10-12 | 15 | 8
QA-301 | Unit Testing - Auth Module | QA | Low | Sarah Connor | Backlog | 2023-10-11 | 2023-10-13 | 8 | 0
DEV-103 | Email Notification Service | Backend | Medium | John Doe | Backlog | 2023-10-14 | 2023-10-16 | 10 | 0