## Sheet
Task ID | Task Description | Assigned To | Priority | Start Date | Due Date | Status | % Complete | Notes
101 | Project Kickoff Meeting | Alice Johnson | High | 2023-10-01 | 2023-10-02 | Completed | 100% | Minutes distributed to team.
102 | Draft UI Mockups | Bob Smith | Medium | 2023-10-03 | 2023-10-10 | In Progress | 45% | Waiting on branding guidelines.
103 | Database Schema Design | Charlie Davis | High | 2023-10-05 | 2023-10-12 | Not Started | 0% | Needs review from lead dev.
104 | QA Testing - Module A | Dana White | Low | 2023-10-15 | 2023-10-20 | Not Started | 0% | Pending development completion.
105 | Client Feedback Review | Alice Johnson | Medium | 2023-10-22 | 2023-10-23 | Not Started | 0% | Scheduled for Monday morning.