## Sheet
Task ID | Task Description | Owner | Start Date | Due Date | Status | % Complete | Priority | Notes / Blockers
101 | Requirement Analysis | John Doe | 2023-10-01 | 2023-10-05 | Completed | 100% | High | Finalized and signed off.
102 | Database Schema Design | Jane Smith | 2023-10-06 | 2023-10-10 | In Progress | 75% | High | Reviewing normalization.
103 | Front-end Mockups | Mike Ross | 2023-10-08 | 2023-10-15 | In Progress | 40% | Medium | Waiting on branding assets.
104 | API Integration | Sarah Lee | 2023-10-12 | 2023-10-20 | Not Started | 0% | High | Delayed due to server migration.
105 | User Acceptance Testing | QA Team | 2023-11-01 | 2023-11-10 | Not Started | 0% | Medium | Pending development completion.