## Sheet
ID | Deliverable Name | Assigned To | Start Date | Due Date | Status | % Complete | Notes
DEL-001 | Project Charter | John Doe | 2023-10-01 | 2023-10-05 | Completed | 100% | Approved by stakeholder.
DEL-002 | UI/UX Wireframes | Jane Smith | 2023-10-06 | 2023-10-20 | In Progress | 65% | Review scheduled for Friday.
DEL-003 | Database Schema | Mike Ross | 2023-10-15 | 2023-10-25 | Not Started | 0% | Pending final requirements.
DEL-004 | API Documentation | Sarah Lee | 2023-10-20 | 2023-11-01 | Not Started | 0% | -