## Sheet
Milestone ID | Deliverable Description | Owner | Target End Date | Actual Completion Date | Status | % Complete | Notes
M1 | Project Charter Approval | Jane Doe | 2023-10-01 | 2023-09-28 | Completed | 100% | Approved by steering committee.
M2 | Requirements Gathering | John Smith | 2023-10-15 | 2023-10-18 | Completed | 100% | Slight delay due to stakeholder availability.
M3 | Design Phase Sign-off | Alice Wong | 2023-11-01 |  | In Progress | 60% | UI mockups are under review.
M4 | Development Sprint 1 | Development Team | 2023-11-20 |  | Not Started | 0% | Pending design sign-off.
M5 | User Acceptance Testing (UAT) | Quality Assurance | 2023-12-05 |  | Not Started | 0%
M6 | Final Deployment | Jane Doe | 2023-12-15 |  | Not Started | 0% | Go-live scheduled for midnight.