## Sheet
Project / Task Name | Assigned To | Start Date | Deadline | Days Remaining | Status | Notes
Website Redesign | Alex Rivera | 2023-10-01 | 2023-11-15 | 12 | In Progress | Awaiting client feedback on hero section.
Q4 Financial Audit | Sarah Chen | 2023-11-01 | 2023-12-01 | 28 | Not Started | Internal review scheduled for next week.
Mobile App Security Patch | Jordan Smith | 2023-10-25 | 2023-10-31 | 3 | Urgent | Critical vulnerability fix.
Logo Design Update | Maria Garcia | 2023-09-15 | 2023-10-20 | 0 | Completed | Final files delivered to marketing.
Server Migration | Tech Team | 2023-11-10 | 2023-11-25 | 22 | In Progress | Backups are currently being generated.