## Sheet
ID | Deliverable Name | Description | Owner | Priority | Start Date | Due Date | Status | % Complete | Notes
001 | Project Charter | Initial project definition document | John Doe | High | 2023-10-01 | 2023-10-05 | Completed | 100% | Approved by stakeholders.
002 | Market Research Report | Analysis of competitor landscape | Jane Smith | Medium | 2023-10-06 | 2023-10-20 | In Progress | 45% | Pending final data from survey.
003 | UI/UX Prototypes | Figma wireframes for mobile app | Mike Ross | High | 2023-10-15 | 2023-11-01 | Not Started | 0% | Waiting for research report.
004 | Budget Approval | Final sign-off on Q4 expenses | Sarah Connor | High | 2023-10-20 | 2023-10-25 | In Progress | 10% | Initial draft submitted.
005 | Testing Plan | QA documentation and test cases | Alex Vance | Low | 2023-11-05 | 2023-11-15 | Not Started | 0%