## Sheet
Phase ID | Phase Name | Owner | Start Date | Target End Date | Progress (%) | Status
P-001 | Requirement Analysis | John Smith | 2023-10-01 | 2023-10-15 | 100% | Completed
P-002 | System Design | Sarah Chen | 2023-10-16 | 2023-11-05 | 75% | In Progress
P-003 | Development Phase 1 | Mike Ross | 2023-11-06 | 2023-12-20 | 10% | In Progress
P-004 | Quality Assurance | Anna White | 2023-12-21 | 2024-01-15 | 0% | Not Started
P-005 | User Acceptance Testing | Client Lead | 2024-01-16 | 2024-01-30 | 0% | Delayed