## Sheet
ID | Task Description | Priority | Status | Assigned To | Start Date | Due Date | % Complete | Notes
101 | Project Kick-off Meeting | High | Completed | John Doe | 2023-10-01 | 2023-10-01 | 100% | All stakeholders attended.
102 | Requirement Gathering | High | In Progress | Jane Smith | 2023-10-02 | 2023-10-10 | 60% | Waiting on client feedback.
103 | UI Design Mockups | Medium | Not Started | Alex Ross | 2023-10-11 | 2023-10-20 | 0% | Pending requirement approval.
104 | Database Architecture | High | In Progress | Mike Chen | 2023-10-05 | 2023-10-15 | 40% | Schema design phase.
105 | Initial Testing Phase | Low | Not Started | Sarah Lee | 2023-10-25 | 2023-11-01 | 0% | Resource allocation pending.