## Sheet
Task ID | Task Description | Priority | Status | Assigned To | Estimated Effort (Hrs) | Actual Effort (Hrs) | Remaining Effort (Hrs) | Sprint Number | Notes
T-001 | Design Database Schema | High | Done | John Doe | 8 | 10 | 0 | 1 | Includes indexing strategy
T-002 | API Authentication Layer | High | In Progress | Jane Smith | 12 | 6 | 6 | 1 | Using OAuth2
T-003 | UI Unit Testing | Medium | To Do | Mike Ross | 16 | 0 | 16 | 1 | Targeting 80% coverage
T-004 | Bug Fix: Login Redirect | Low | Review | Sarah Connor | 4 | 3 | 1 | 1 | Waiting for QA approval
T-005 | Documentation | Low | To Do | Unassigned | 5 | 0 | 5 | 1 | Finalizing API docs