## Sheet
Task ID | Task Description | Category | Assigned To | Priority | Status | Start Date | Due Date | % Complete | Est. Hours | Actual Hours | Dependencies
T-101 | Project Kick-off Meeting | Planning | Alice Johnson | Medium | Completed | 2023-10-01 | 2023-10-01 | 100% | 2 | 2.5 | None
T-102 | Database Schema Design | Development | Bob Smith | High | In Progress | 2023-10-02 | 2023-10-10 | 45% | 16 | 8 | T-101
T-103 | UI Mockup Creation | Design | Charlie Davis | Medium | Not Started | 2023-10-05 | 2023-10-12 | 0% | 10 | 0 | T-101
T-104 | API Integration | Development | Bob Smith | High | Blocked | 2023-10-11 | 2023-10-20 | 5% | 20 | 1 | T-102
T-105 | Final QA Testing | QA | Dana White | Urgent | Review | 2023-10-25 | 2023-10-30 | 0% | 12 | 0 | T-104