## Sheet
Task ID | Task Description | Assigned To | Priority | Status | Start Date | Due Date | Notes
101 | Project Kick-off Meeting | John Doe | High | Completed | 2023-10-01 | 2023-10-01 | All stakeholders attended.
102 | Requirements Gathering | Jane Smith | High | In Progress | 2023-10-02 | 2023-10-10 | Drafting functional specs.
103 | UI Design Mockups | Alex Rivera | Medium | Not Started | 2023-10-11 | 2023-10-20 | Pending requirement sign-off.
104 | Database Schema Setup | Sam Wilson | Medium | Not Started | 2023-10-15 | 2023-10-18
105 | API Integration | Jane Smith | High | Not Started | 2023-10-21 | 2023-10-30