## Sheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Status | % Complete | Notes
101 | Project Initiation | John Doe | 2023-10-01 | 2023-10-05 | 5 | Completed | 100% | Initial kickoff meeting held.
102 | Requirement Analysis | Jane Smith | 2023-10-06 | 2023-10-15 | 10 | In Progress | 60% | Stakeholder interviews ongoing.
103 | System Design | Mike Ross | 2023-10-16 | 2023-10-30 | 14 | Not Started | 0% | Pending requirement sign-off.
104 | Development Phase 1 | Sarah Connor | 2023-11-01 | 2023-11-20 | 19 | Not Started | 0% | Back-end infrastructure.
105 | User Testing | QA Team | 2023-11-21 | 2023-11-30 | 9 | Not Started | 0% | Final validation before launch.