## Sheet
ID | Milestone Description | Assigned To | Start Date | Target Date | Actual End Date | Completion (%) | Status
001 | Project Initiation & Kickoff | John Doe | 2023-10-01 | 2023-10-05 | 2023-10-04 | 100% | Completed
002 | Requirement Gathering | Jane Smith | 2023-10-06 | 2023-10-15 | 2023-10-16 | 100% | Completed
003 | Design Phase | Mike Ross | 2023-10-17 | 2023-11-01 | - | 65% | In Progress
004 | Backend Development | Sarah Connor | 2023-11-02 | 2023-12-15 | - | 10% | In Progress
005 | Quality Assurance Testing | Alex Vance | 2023-12-16 | 2023-12-30 | - | 0% | Delayed