## Sheet
Client Name | Account Manager | Onboarding Stage | Start Date | Target Go-Live | Completion % | Status | Notes
Acme Corp | John Smith | Technical Setup | 2023-10-01 | 2023-11-15 | 45% | In Progress | Waiting on API credentials from client.
Global Industries | Sarah Jenkins | Training | 2023-09-15 | 2023-10-20 | 90% | In Progress | Final user walkthrough scheduled for Friday.
Starlight Retail | Michael Chen | Post-Launch Review | 2023-08-20 | 2023-09-30 | 100% | Completed | Handed over to Support team.
TechFlow Solutions | John Smith | Data Migration | 2023-10-10 | 2023-12-01 | 10% | At Risk | Data format issues; meeting set for Monday.
Summit Logistics | Sarah Jenkins | Kick-off | 2023-11-01 | 2023-12-15 | 5% | Not Started | Introductory call completed.